## Cover
DCAA Audit Program
Structured Audit Step Analysis
Activity Code | 10100
Program | Post Year End Incurred Cost Audit - Small
Version | 6.5
Date | Jan 2026
Variant | Small
Total Sections | 10
Total Audit Steps | 114
Generated March 27, 2026
GovConDash.ai ¦ Government Contracts, Simplified
www.govcondash.ai

## Instructions
Instructions
How to use the Audit Steps tab and data definitions
How to Use the Audit Steps Tab
Navigation | Use the frozen header row and auto-filter dropdowns (row 3) to sort and filter by any column. Click the dropdown arrow on any column header to filter to specific values.
Filtering by Section | Use the Audit Section filter to focus on a specific audit area (e.g., "B-01 Preliminary Steps", "H-01 Indirect Expenses"). Sections are sorted in DCAA audit program order.
Searching Steps | Use Excel's Find & Replace (Ctrl+F) to locate specific audit steps, regulation references, or keywords. The Description column contains the full text of each audit step.
Using Keywords | The Keywords column categorizes each step by topic area. Filter on keywords to find all steps related to a specific concern (e.g., "compliance critical", "executive comp").
Regulation Cross-Reference | The Regulation References and CAM References columns let you trace each audit step back to its authoritative source. Filter these columns to find all steps tied to a specific FAR, CAS, or CAM section.
Print Setup | The sheet is pre-configured for landscape printing with the header row repeated on each page. Use File > Print to preview.
Column Definitions (Data Dictionary)
Activity Code | The DCAA 5-digit activity code that uniquely identifies the audit program (e.g., 10100 for Incurred Cost audits). This code corresponds to DCAA's audit assignment system.
Doc Type | Document type indicator. "AP" denotes an Audit Program — the standard DCAA planning document that outlines required audit procedures for a specific cost element or functional area.
Version No | The version number of the audit program as published by DCAA (e.g., 12.5). Higher versions reflect updated procedures, regulatory changes, or lessons learned.
Date | The publication or effective date of the audit program version (e.g., "July 2024"). Auditors should verify they are using the most current version.
Program Description | The full descriptive title of the audit program (e.g., "Incurred Cost Audit — Small"). Indicates the scope and focus area of the program.
Audit Section | The major section identifier and title within the audit program (e.g., "B-01 Preliminary Steps", "H-01 Indirect Expenses"). Sections are lettered A–Z and numbered, with B sections being preliminary/planning steps and A sections being concluding steps.
Audit Subsection | A subdivision within a section that groups related audit steps (e.g., "Understanding and Planning", "Design Testing Plan", "Evaluation"). Not all sections have subsections.
Audit Step | The sequential step number within its section (e.g., "1", "2", "3a."). Letter suffixes (a., b., c.) indicate sub-steps under a parent step. Steps are ordered as they appear in the original DCAA audit program.
Description | The full text of the audit procedure to be performed. This is the primary content extracted from the DCAA audit program and describes the specific action the auditor must take, including what to examine, verify, test, or document.
Keywords | Auto-generated topical categories assigned to each step based on its description content. See the Keywords Reference section below for comprehensive details on each keyword category.
Regulation References | Federal regulations cited in the audit step description. Includes FAR (Federal Acquisition Regulation), DFARS (Defense Federal Acquisition Regulation Supplement), and CAS (Cost Accounting Standards) references. These trace each procedure to its regulatory authority.
CAM References | References to the DCAA Contract Audit Manual (CAM) cited in the audit step. The CAM provides DCAA's official audit guidance and procedures. See: https://www.dcaa.mil/Guidance/CAM-Contract-Audit-Manual/
Keywords Reference — Comprehensive Details
Keywords are automatically assigned to each audit step by analyzing the description text against curated pattern libraries. They fall into five groups: Audit Focus Areas, Cost Elements, Regulatory Compliance, Contractor Risk Areas, and Proposal-Specific topics.
── AUDIT FOCUS AREAS ──
high risk | Steps addressing material risks, significant deficiencies, fraud indicators, noncompliance, or internal control weaknesses. These steps require heightened professional skepticism.
audit preparation | Procedural steps involving testing, verification, examination, review, analysis, evaluation, or substantive testing. Core audit execution activities.
documentation required | Steps requiring the auditor to document findings, obtain evidence, gain an understanding, or maintain/retain supporting workpapers.
compliance critical | Steps focused on cost allowability, allocability, and reasonableness determinations — the three pillars of FAR 31.201-2 cost principles. Includes unallowable and questioned cost identification.
cost accounting | Steps related to cost calculations, rate computations, reconciliations, and accounting system evaluations. Covers incurred costs, claimed amounts, and expense categorization.
contract terms | Steps examining contract provisions, subcontract agreements, modifications, clauses, and other contractual terms that affect cost allowability.
compensation limits | Steps evaluating executive compensation, salary caps, bonuses, benefits, pension costs, and FAR/DFARS compensation ceilings (e.g., FAR 31.205-6(p) benchmark compensation).
system requirements | Steps assessing internal controls, accounting systems, timekeeping procedures, and company policies. Relates to DFARS 252.242-7006 accounting system adequacy.
audit sampling | Steps involving sample selection, statistical or judgmental sampling, population analysis, and extrapolation of sample results to the population.
findings potential | Steps that may lead to audit findings, questioned costs, sustained costs, unsupported costs, or penalty recommendations. Relates to report drafting and opinion formation.
audit process | Steps related to audit planning, materiality determination, scope decisions, entrance/exit conferences, fieldwork procedures, and walkthrough testing.
dcaa coordination | Steps requiring coordination with contracting officers, administrative contracting officers (ACOs), cognizant audit offices, or procurement officials.
proposal preparation | Steps specific to evaluating incurred cost proposals, final indirect cost rate submissions, and adequacy determinations per DFARS 252.216-7002.
rate development | Steps examining indirect cost rate calculations including overhead, G&A, fringe benefit, and escalation rates. Covers provisional billing rate analysis.
cost segregation | Steps evaluating the allocation of costs between direct and indirect categories, allocation base selection, cost pool composition, and proper cost segregation.
record keeping | Steps reviewing books of account, general ledgers, journal entries, supporting documentation, and audit trail adequacy.
penalties avoidance | Steps related to expressly unallowable cost penalties (FAR 42.709), false claims, certification requirements, and mischarge identification.
── COST ELEMENTS ──
labor costs | Steps examining labor/personnel costs including hourly rates, timesheets, payroll records, and employee compensation. The largest cost element in most government contracts.
material costs | Steps reviewing material purchases, inventory valuations, supply costs, procurement actions, and vendor pricing. Covers FAR 31.205-26 material costs.
subcontract costs | Steps auditing subcontractor costs, consultant fees, teaming arrangement expenses, and vendor/supplier charges. Includes consent-to-subcontract evaluations.
indirect costs | Steps examining overhead, G&A, fringe benefits, and facilities capital cost of money (FCCM). Covers indirect cost pool composition and allocation base selection.
other direct costs | Steps reviewing ODCs such as travel, equipment, consultant costs, and training expenses. Costs charged directly to contracts outside of labor and materials.
inter org transfers | Steps evaluating inter-organizational transfers (IOTs), corporate/home office allocations, and charges between divisions or affiliates of the same company.
── REGULATORY COMPLIANCE ──
far compliance | Steps citing specific FAR (Federal Acquisition Regulation) sections, particularly FAR Part 31 (Contract Cost Principles) and FAR Part 52 (Solicitation Provisions and Contract Clauses).
cas compliance | Steps related to Cost Accounting Standards (CAS), disclosure statements, and consistency requirements. Applicable to CAS-covered contracts per 48 CFR Chapter 99.
cam reference | Steps citing the DCAA Contract Audit Manual (CAM), which provides DCAA's official audit guidance, procedures, and policy. The full CAM is available at: https://www.dcaa.mil/Guidance/CAM-Contract-Audit-Manual/
gagas standards | Steps referencing Generally Accepted Government Auditing Standards (GAGAS), also known as the "Yellow Book". These standards govern the conduct of government audits.
dfars requirements | Steps citing DFARS (Defense Federal Acquisition Regulation Supplement) provisions, particularly DFARS 252.x clauses applicable to defense contracts.
── CONTRACTOR RISK AREAS ──
executive comp | Steps evaluating executive/officer compensation, key personnel costs, benchmark reasonableness testing, and compliance with FAR 31.205-6(p) compensation caps.
cost transfers | Steps examining cost transfers, reclassifications, journal entry adjustments, and reallocations between cost objectives. A common area for mischarging risk.
billing accuracy | Steps verifying billing accuracy, invoice support, proper charging, and identification of potential mischarges or cross-charges between contracts.
time reporting | Steps reviewing timekeeping systems, labor hour reporting, effort documentation, and timesheet accuracy. Critical for labor-intensive contracts.
cost principles | Steps citing specific FAR 31.2xx cost principles (e.g., 31.201 composition of total cost, 31.202 direct costs, 31.203 indirect costs, 31.205 selected costs).
DCAA Contract Audit Manual (CAM)
The DCAA Contract Audit Manual (CAM) is the authoritative guidance used by DCAA auditors to perform contract audits. It provides detailed procedures, policies, and technical guidance for each audit area. The CAM References column in the Audit Steps tab cites specific CAM sections relevant to each audit step. Contractors can use these references to understand the audit procedures that will be applied to their cost submissions. Access the full CAM online at: https://www.dcaa.mil/Guidance/CAM-Contract-Audit-Manual/
GovConDash.ai ¦ Government Contracts, Simplified

## Audit Steps
GovConDash.ai |  |  | Activity 10100 ¦ Post Year End Incurred Cost Audit - Small ¦ v6.5 | [6 empty] | Small Program
Activity Code | Doc Type | Version No | Date | Program Description | Audit Section | Audit Subsection | Audit Step | Description | Keywords | Regulation References | CAM References
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Planning Considerations |  | 1 | Type of Service - Attestation Examination Engagement
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Initial Planning | 1 | Final Indirect Cost Proposal a. Review the "Checklist for Determining Adequacy of Contractor Incurred Cost Proposal' completed during the adequacy review of the incurred cost proposal and note any areas requiring further consideration. b. Review the completed risk-based sampling eligibility determination tool, if applicable. | audit preparation, audit sampling, cost accounting, cost segregation, high risk, indirect costs, proposal preparation, rate development
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Planning Considerations |  | 2 | Audit Specific Independence Determination
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Initial Planning | 2 | Identify and contact the contracting officer to notify them of the commencement of audit. a. Discuss any significant concerns or other information that the contracting officer may have relevant to the audit (e.g., risk related to the contractor's financial condition, statute of limitation dates, significant prior findings, risk-based sampling eligibility determination, contracts that are in overrun position for potential mischarging, etc.) that will impact the audit and adjust the audit scope and procedures accordingly. b. Request the identification of any closed contracts or settled terminations. | audit process, audit sampling, dcaa coordination, executive comp, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Initial Planning | 3 | Review of Permanent Files and Audit Leads Using the framework of WP B-04, review EPIC for audit leads and contractor permanent files to determine if there are areas of risk or potential material misstatement that should be considered when designing audit procedures, this includes prior assignments . | audit preparation, high risk, material costs
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Initial Planning | 4 | Management Inquiries During the entrance conference or other appropriate meeting make the GAGAS required inquiries of contractor management. Using the framework of WP B-05, document the contractor's response, and identify areas of risk and the impact to the audit scope. | audit process, documentation required, gagas standards, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Initial Planning | 5 | Obtain and document an understanding of contractor internal controls relevant to the overall submission. (For significant cost elements, auditors may obtain this understanding per cost element during the individual walkthroughs.) | cost accounting, documentation required, high risk, proposal preparation
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Initial Planning | 6 | Fraud Risk Indicators Using the framework in WP B-09, discuss the fraud risk indicators with the audit team. RECONCILIATIONS | high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Reconciliations | 7 | Cost Reconciliation to books. Verify the Direct and Indirect costs reconcile to the contractor's general ledger or other accounting system records that will aid in the evaluation of the subject matter. | audit preparation, cost accounting, cost segregation, indirect costs, rate development, record keeping, system requirements
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Reconciliations | 8 | Voluntary Deletions Reconcile voluntary deleted items identified in the incurred cost proposal to the books and records and ensure all voluntary deleted account balances are identified and accounted for as unclaimed, including directly associated unallowable costs in accordance with FAR 31.201-6. Identify potential directly associated unallowable costs that may not have been removed from the proposal for consideration in planning transaction testing. SCOPE OF AUDIT AND MATERIALITY | audit process, compliance critical, cost accounting, cost principles, far compliance, proposal preparation, record keeping | FAR 31.201, FAR 31.201-6
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Scope Of Audit And Materiality | 9 | Adjusting Entries Evaluate adjusting journal entries or exception reports focusing on changes between contracts and or CLINS, or direct and indirect costs. Identify additional areas to follow up on. | audit preparation, cost segregation, indirect costs, rate development, record keeping
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Scope Of Audit And Materiality | 10 | Dollars Examined and Total Subject Matter of Audit
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Scope Of Audit And Materiality | 11 | Calculate dollars examined and the total subject matter of audit (CAM 6- 107.2b) using the framework of WP B-06. | cam reference |  | CAM 6- 107.2b
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Scope Of Audit And Materiality | 11 | Government Participation Use the framework ofWP B-07 to review the contractor's calculation and determine Government flexibly priced contract percentages (Government participation) of the indirect expense base(s). | audit preparation, contract terms, cost accounting, cost segregation, indirect costs, rate development
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Scope Of Audit And Materiality | 12 | Materiality Assessment Using the framework of WP B-07, perform the following procedures to assess materiality: a. Calculate quantified materiality using the materiality formula (CAM 6- 107.2(a)) and the total subject matter of audit calculated in B-06 . b. Calculate adjusted materiality for significant direct and indirect cost elements (CAM 6-107.1(c)) and identify for further audit procedures: • accounts that exceed the adjusted materiality amount; and • accounts with values less than the thresholds that are significant based on risk factors, qualitative characteristics, variability, and/or other stated concerns of the contracting officer. AUDIT CRITERIA | audit preparation, audit process, cam reference, cost accounting, cost segregation, dcaa coordination, executive comp, high risk, indirect costs, rate development |  | CAM 6- 107.2, CAM 6-107.1
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Scope Of Audit And Materiality | 12b. | Calculate adjusted materiality for significant direct and indirect cost elements (CAM 6-107.1(c)) and identify for further audit procedures: • accounts that exceed the adjusted materiality amount; and • accounts with values less than the thresholds that are significant based on risk factors, qualitative characteristics, variability, and/or other stated concerns of the contracting officer. | audit process, cam reference, cost accounting, cost segregation, dcaa coordination, executive comp, high risk, indirect costs, rate development |  | CAM 6-107.1
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Audit Criteria | 13 | Significant Contract Terms or Provisions Using the framework of WP B-08, determine if contract briefs contain significant contract terms or provisions that impact the audit scope and design appropriate additional audit procedures. • For contracts ready to close, plan testing to identify any amounts incurred outside the period of performance. Verify that the total amount claimed does not exceed the lesser of the total allowable costs and fee or the funding limitation per the contract brief or per the contract and latest modification. RISK ASSESSMENT SUMMARY | audit preparation, audit process, compliance critical, contract terms, cost accounting, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Risk Assessment Summary | 14 | Assess and document the need for technical or other audit assistance. • If material flexibly-priced subcontracts or IOTs are identified B-06 assess the need for assist audits in coordination with the cognizant auditors of the lower-tier subcontractors. • Coordinate with Field Detachment as necessary. | audit preparation, dcaa coordination, documentation required, high risk, material costs
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Risk Assessment Summary | 15 | Entrance Conference Conduct an entrance conference, include a sign-in sheet with all attendees at the meeting, and discuss the following: | audit process
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Risk Assessment Summary | 16 | Electronically transmit an acknowledgement letter and notification memo to the appropriate Contracting Officer and the Contractor to formally notify them of the audit and expected completion date in accordance with CAM 4-104. | cam reference, dcaa coordination, executive comp |  | CAM 4-104
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | B-01 Preliminary Steps | Risk Assessment Summary | 17 | Summarize in WP B the results and accounts/cost amounts that will be subject to further audit procedures to support the audit opinion. | cost accounting, documentation required, findings potential
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Understanding and Planning | 1 | Obtain and document an understanding of contractor's internal controls related to labor. • Consideration should be given to any changes in policies for direct/indirect charging since the last accounting system audit or incurred cost audit. | cost accounting, cost segregation, documentation required, indirect costs, labor costs, proposal preparation, rate development, system requirements
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Understanding and Planning | 2 | Determine and document the reliability of the information the audit team will use to reach their conclusions in this section. | documentation required
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Understanding and Planning | 3 | Perform an analysis of the contractor's labor. Below are suggestions that can be utilized to perform this analysis but are not mandatory. • Comparative Analysis - compare current year labor to prior year(s) labor to determine if there are significant changes. • If there are significant T&Mcontracts, perform a profit margin test. Design Testing Plan: | audit preparation, high risk, labor costs
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Design Testing Plan | 4 | Design testing plan using the steps below. • Based on the risk assessment and the understanding and analysis performed above, the steps below should be modified to reflect detailed testing that needs to be completed to express an opinion. The steps below cover basic audit steps for labor but may not be applicable to your audit based on the analysis and understanding performed above. Evaluation: | documentation required, findings potential, high risk, labor costs
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Evaluation | 5 | Perform substantive analytical procedures based on materiality and risk. | audit preparation, audit process, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Evaluation | 6 | If real-time testing of labor was performed for the year under audit, document the sufficiency of the procedures performed. • Coordinate with Field Detachment as necessary to address labor costs on classified contracts | dcaa coordination, documentation required, labor costs, time reporting
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Evaluation | 7 | Perform test of details for labor costs including both labor hours and labor rates. • This should include the Reasonableness of Non-Executive Compensation (including bonuses and awards): If indicated by the materiality and risk assessment. | audit preparation, audit process, compensation limits, executive comp, high risk, labor costs
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Evaluation | 8 | ForT&M or Labor Hour contracts, based on the preliminary steps, select a sample of contracts for testing of details to include position qualifications. | audit sampling, labor costs, time reporting
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Evaluation | 9 | Executive Compensation ( only if material ): a. Trace the executive compensation costs to the appropriate G&A and overhead accounts to ensure that all the executive compensation is being evaluated for reasonableness (including bonuses and awards). b. Perform sufficient steps to verify that all allocable direct and indirect executive compensation in excess of the statutory compensation ceilings (seeCAM 6-414) has either been appropriately: (i) excluded from the contractor's incurred cost submission, or (ii) identified as expressly unallowable costs and questioned in the audit report. If additional assistance is required, see section U and refer to the Agency Compensation Team. Summarize Results | audit preparation, compensation limits, compliance critical, cost accounting, cost segregation, executive comp, findings potential, high risk, indirect costs, material costs, penalties avoidance, proposal preparation, rate development
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Evaluation | 9b. | Perform sufficient steps to verify that all allocable direct and indirect executive compensation in excess of the statutory compensation ceilings (seeCAM 6-414) has either been appropriately: (i) excluded from the contractor's incurred cost submission, or (ii) identified as expressly unallowable costs and questioned in the audit report. If additional assistance is required, see section U and refer to the Agency Compensation Team. | audit preparation, compensation limits, compliance critical, cost accounting, cost segregation, executive comp, findings potential, indirect costs, penalties avoidance, proposal preparation, rate development
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Summarize Results | 10 | Verify that any questioned labor related costs also consider directly associated costs that should also be excluded/questioned. (FAR 31.201- 6(a)) | audit preparation, compliance critical, cost principles, far compliance, findings potential, labor costs | FAR 31.201
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | D-01 Direct and Indirect Labor | Summarize Results | 11 | Summarize the results including the conclusions, basis of proposed cost, and audit evaluation. | cost accounting
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | E-01 Direct Material | Understanding and Planning | 1 | Obtain and document an understanding of contractor internal controls related to material. • Consideration should be given to any changes in policies for allocating and accumulating costs since the last accounting system audit or incurred cost audit. | cost accounting, documentation required, high risk, material costs, proposal preparation, system requirements
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | E-01 Direct Material | Understanding and Planning | 2 | Determine and document the reliability of the information the audit team will use to reach their conclusions in this section. | documentation required
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | E-01 Direct Material | Understanding and Planning | 3 | Perform an analysis of the contractor's direct material. Below is a suggestion that can be utilized to perform this analysis but is not mandatory. • Comparative Analysis - compare current year material costs to prior year(s) material costs to determine if there are significant changes. Design Testing Plan | audit preparation, cost segregation, high risk, material costs
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | E-01 Direct Material | Design Testing Plan | 4 | Design testing plan using the steps below. • Based on the risk assessment and the understanding and analysis performed above, the steps below should be modified to reflect the evaluation of detailed testing that needs to be completed to express an opinion. The steps below cover basic audit steps but may not be applicable to your audit based on the analysis and understanding performed above. Evaluation | documentation required, findings potential, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | E-01 Direct Material | Evaluation | 5 | Perform substantive analytical procedures based on materiality and risk. | audit preparation, audit process, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | E-01 Direct Material | Evaluation | 6 | Real-time Testing of Purchases Existence and Consumption (CAM 6- 305.3a). If applicable, review and incorporate the results of real-time testing. • Coordinate with Field Detachment as necessary to address material costs on classified contracts. | audit preparation, cam reference, dcaa coordination, high risk, material costs, time reporting |  | CAM 6- 305.3a
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | E-01 Direct Material | Evaluation | 7 | Perform test of details for material costs including allocability and reasonableness for quantity and price. Determine if testing to payment is necessary. Summarize Results | audit preparation, executive comp, high risk, material costs
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | E-01 Direct Material | Summarize Results | 8 | Verify that any questioned direct material costs also consider directly associated costs that should also be excluded/questioned (FAR 31.201- 6(a)). | audit preparation, compliance critical, cost principles, cost segregation, far compliance, findings potential, high risk, material costs | FAR 31.201
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | E-01 Direct Material | Summarize Results | 9 | Summarize the results including the conclusions, basis of proposed cost, and audit evaluation. | cost accounting
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Understanding and Planning | 1 | Obtain and document an understanding of contractor internal controls related to subcontractor costs. • Consideration should be given to any changes in policies for allocating and accumulating costs since the last accounting system audit or incurred cost audit. | cost accounting, documentation required, proposal preparation, subcontract costs, system requirements
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Understanding and Planning | 2 | Determine and document the reliability of the information the audit team will use to reach their conclusions in this section. | documentation required
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Understanding and Planning | 3 | Perform an analysis of the contractor's subcontract costs. Below are suggestions that can be utilized to perform this analysis but are not mandatory. • Comparative Analysis - compare current year subcontractor costs to prior year(s) subcontractor costs to determine if there are significant changes. • Perform an excessive passthrough analysis to determine if any of the contracts have incurred 70% or more pass-through subcontract costs. Design Testing Plan | audit preparation, contract terms, cost accounting, high risk, subcontract costs
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Design Testing Plan | 4 | Design testing plan using the steps below. • Based on the risk assessment and the understanding and analysis performed above, the steps below should be modified to reflect the evaluation of detailed testing that needs to be completed to express an opinion. The steps below cover basic audit steps but may not be applicable to your audit based on the analysis and understanding performed above. Evaluation | documentation required, findings potential, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Evaluation | 5 | Perform substantive analytical procedures based on materiality and risk. | audit preparation, audit process, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Evaluation | 6 | Assess allowability (FAR 31.201-2) for selected subcontracts (including fixed priced subcontracts and those flexibly priced subcontracts that assist audits were requested for) issued under flexibly priced prime contracts / upper-tier subcontracts. • Coordinate with Field Detachment as necessary to address subcontract costs on classified contracts. | audit preparation, contract terms, cost principles, dcaa coordination, far compliance, subcontract costs | FAR 31.201, FAR 31.201-2
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Evaluation | 6a. | Determine if the subcontract costs are allocable (FAR 31.201-4) to the prime contract (i.e. was effort consistent with (sub)contract requirements, is the subcontract SOW consistent with prime contract, etc.?) | compliance critical, contract terms, cost principles, far compliance, subcontract costs, time reporting | FAR 31.201, FAR 31.201-4
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Evaluation | 6b. | Determine if subcontract costs are reasonable (FAR 31.201-3) at prime contract level. [Note: For some subcontracts, this could have been previously tested in prior incurred costs audits or during the price proposal audit. Reliance should be placed on prior audits to the maximum extent possible.] | compliance critical, contract terms, cost accounting, cost principles, far compliance, proposal preparation, subcontract costs | FAR 31.201, FAR 31.201-3
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Evaluation | 7 | If assist audits were received, address any significant questioned costs in the assist audit report that pertain to your contracts with the prime or upper-tier contractor. Obtain the prime or upper-tier contractor's position on the questioned costs. Incorporate the questioned costs after considering prime / upper-tier contractor's position. Follow-up on requested assist audits that have not been received. | compliance critical, dcaa coordination, documentation required, findings potential, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Evaluation | 8 | Excessive Pass through Charges (FAR 52.215-23, previously DFARS 252.215-7004, the DFARS clause became effective for all contracts awarded after 4/26/2007 and the FAR clause became effective 10/14/2009). Contractors are required to identify the percentage of work that will be subcontracted. When the percentage of total subcontract effort is greater than 70 percent of the total work to be performed (at total contract level), the contractor must provide information supporting the value it adds with regard to the subcontracted work. Ensure the submission does not include unallowable excessive pass-through charges in accordance with FAR 52.215-22 and FAR 52.215-23. a. If the contract contains FAR 52.215-23 Alternate I, the contracting officer made a determination at the time of award that the prospective contractor has demonstrated that its functions provide added value to the contracting effort and there are no excessive pass-through charges. Auditors should: • Compare the contractor demonstrated value added functions with those disclosed to the contracting officer at the time of award to ensure the functions billed or incurred are consistent with the contracting officer's determination; and • Ensure the disclosed value-added functions were performed and are reasonable. b. If the contract does not contain FAR Alternate I, the auditor perform procedures to determine if the contractor incurred excessive pass through charges as defined in FAR 52.215-23. • Request the contractor to identify the value added functions it provided consistent with the definition in the contract clause. • Verify the disclosed functions were performed, are reasonable and represent value added effort. • FAR 52.215-23(c) requires the contractor to notify the Contracting Officer if there are changes in subcontract effort after award that results in it exceeding 70% of total contract value. The auditor should request the contractor to provide evidence of written notification to the contracting officer that more than 70 percent of the total costs of the work to be performed by subcontractors. If the contractor did not comply with this requirement, the auditor | audit preparation, compliance critical, contract terms, cost accounting, dcaa coordination, dfars requirements, documentation required, executive comp, far compliance, proposal preparation, record keeping, subcontract costs, time reporting | DFARS 252.215, DFARS 252.215-7004, FAR 52.215, FAR 52.215-22, FAR 52.215-23
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Evaluation | 8b. | If the contract does not contain FAR Alternate I, the auditor perform procedures to determine if the contractor incurred excessive pass through charges as defined in FAR 52.215-23. | audit preparation, contract terms, cost accounting, far compliance | FAR 52.215, FAR 52.215-23
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Evaluation | 8c. | If the functions were not performed or add no or negligible value to the contract, then the indirect costs added by the prime contractor to the subcontracted work should be questioned as excessive pass through charges in accordance with FAR 31.203(i). | compliance critical, contract terms, cost principles, cost segregation, far compliance, findings potential, indirect costs, rate development | FAR 31.203
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Summarize Results | 9 | Verify that any questioned subcontractor costs also consider directly associated costs that should also be excluded/questioned. (FAR 31.201- 6(a)) | audit preparation, compliance critical, cost principles, far compliance, findings potential, subcontract costs | FAR 31.201
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | F-01 Subcontracts | Summarize Results | 10 | Summarize the results including the conclusions, basis of proposed cost, and audit evaluation. | cost accounting
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | G-01 Other Direct Costs (ODC) | Understanding and Planning | 1 | Obtain and document an understanding of contractor internal controls related to other direct costs. • Consideration should be given to any changes in policies for allocating and accumulating costs since the last accounting system audit or incurred cost audit. | cost accounting, cost segregation, documentation required, other direct costs, proposal preparation, system requirements
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | G-01 Other Direct Costs (ODC) | Understanding and Planning | 2 | Determine and document the reliability of the information the audit team will use to reach their conclusions in this section. | documentation required
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | G-01 Other Direct Costs (ODC) | Understanding and Planning | 3 | Perform an analysis of the contractors Other Direct Costs (ODC). Below is a suggestion that can be utilized to perform this analysis but are not mandatory. • Comparative Analysis - compare current year other direct costs to prior year(s) other direct costs to determine if there are significant changes. Design Testing Plan | audit preparation, cost segregation, high risk, other direct costs
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | G-01 Other Direct Costs (ODC) | Design Testing Plan | 4 | Design testing plan using the steps below. • Based on the risk assessment and the understanding and analysis performed above, the steps below should be modified to reflect the evaluation of detailed testing that needs to be completed to express an opinion. The steps below cover basic audit steps but may not be | documentation required, findings potential, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | G-01 Other Direct Costs (ODC) | Evaluation | 5 | Perform substantive analytical procedures based on materiality and risk. | audit preparation, audit process, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | G-01 Other Direct Costs (ODC) | Evaluation | 6 | For selected transactions, perform test of details including allocability and reasonableness. Determine if testing to payment is necessary. • Coordinate with Field Detachment as necessary to address ODCs on classified contracts. Summarize Results | audit preparation, dcaa coordination, executive comp
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | G-01 Other Direct Costs (ODC) | Summarize Results | 7 | Verify that any questioned other direct cost also considers directly associated costs that should also be excluded/questioned (FAR 31.2016(a)). | audit preparation, compliance critical, cost accounting, cost segregation, far compliance, findings potential, other direct costs | FAR 31.2016, FAR 31.2016(a
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | G-01 Other Direct Costs (ODC) | Summarize Results | 8 | Summarize the results including the conclusions, basis of proposed cost, and audit evaluation. | cost accounting
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Understanding and Planning | 1 | Obtain and document an understanding of contractor internal controls related to Indirect Expenses. • Document any changes in policies for direct/indirect charging since the last accounting system audit or incurred cost audit. | cost accounting, cost segregation, documentation required, indirect costs, proposal preparation, rate development, system requirements
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Understanding and Planning | 2 | Determine and document the reliability of the information the audit team will use to reach their conclusions in this section. | documentation required
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Understanding and Planning | 3 | General Ledger, Trial Balance, Income and/or Credit Adjustments (CAM 6-608.2d (5)). Document your understanding of the types of income and credits occurring at this contractor, and your understanding of the contractor's methods for accounting for income and credits. • Analyze the contractor's general ledger, trial balance and entries to profit accounts and other income accounts to identify any credits or income that have not been accounted for which the government may be entitled to a credit. Examples include purchase discounts, scrap sales, rental income, excessive company reserves, insurance and state tax rebates and refunds, etc. Identify adjustments requiring follow-up. | audit preparation, cam reference, cost accounting, documentation required, material costs, record keeping |  | CAM 6-608.2d
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Understanding and Planning | 4 | Perform an analysis of the contractor's indirect rates. Below are suggestions that can be utilized to perform this analysis but are not mandatory. • Comparative Analysis - compare current year pool and base amounts to prior years amounts to determine if there are significant changes. • Relationship Analysis Design Testing Plan | audit preparation, cost segregation, high risk, indirect costs, rate development
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Design Testing Plan | 5 | Design testing plan using the steps below. • Based on the risk assessment and the understanding and analysis performed above, the steps below should be modified to reflect the evaluation of detailed testing that needs to be complete to express an opinion. The steps below cover basic audit steps but may not be applicable to your audit based on the analysis performed above. Evaluation | documentation required, findings potential, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Evaluation | 6 | Perform substantive analytical procedures based on materiality and risk. | audit preparation, audit process, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Evaluation | 7 | Perform test of details for expenses to obtain sufficient evidence for allowability, allocability, and reasonableness of these costs. Determine if testing to payment is necessary. OTHER PROCEDURES THAT MAY NEED TO BE PERFORMED [Note: These steps may not be applicable for the majority of small contractors. Discuss with your supervisor and obtain approval prior to performing these steps.] | audit preparation, documentation required, executive comp
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Evaluation | 8 | Cost of Money - Based on materiality and the analysis above verify the amounts on the CASB-CMF form, Facilities Capital Cost of Money Factors Computation, to source documents and verify the accuracy of the contractor's calculations. Ensure the contractor used applicable cost of money rate for that FY from (https://www.fiscal.treasury.gov/prompt-payment/rates.html). (CAM 8-414.2). | audit preparation, audit process, cam reference, cost accounting, indirect costs, labor costs, rate development | CASB-CMF | CAM 8-414.2
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Evaluation | 9 | Indirect Cost Limitation for Basic Research Awards: Review the contractor briefs to ascertain the contractor's 'basic research' awards and the applicable FY appropriated funds paid. If the contractor has Basic Research Awards, see CAM 6-612. | audit preparation, cam reference, cost accounting, cost segregation, indirect costs, rate development |  | CAM 6-612
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Evaluation | 10 | Pension Costs. Pension costs are audited by the FAO cognizant of the contractor location where the plans are administered and the costs are incurred. For multi-segment contractors, this will generally be the corporate home office. Therefore, divisional auditors may need to request an assist audit from the FAO cognizant of the corporate home office. a. If the costs are auditable at your location and significant, (i.e., material and/or risk factors have been identified) develop an audit program considering the FAR and CAS requirements (e.g., relevant audit steps may be considered from the CAS compliance audit programs). Identify any terminated pension plan costs or credits on the books for this contractor or for acquired or absorbed divisions or other division employees for further review. b. If the costs are significant (i.e., material and or risk factors have been identified), test contractor contributions under employee pension plans to evidence of payment (i.e., contractor bank statements, electronic funds transfer, or third party payroll processor records). | audit preparation, cas compliance, compensation limits, compliance critical, cost accounting, cost transfers, dcaa coordination, documentation required, high risk, inter org transfers, labor costs, material costs, record keeping | CAS compliance, CAS requirements, FAR and CAS requirements
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Evaluation | 10a. | If the costs are auditable at your location and significant, (i.e., material and/or risk factors have been identified) develop an audit program considering the FAR and CAS requirements (e.g., relevant audit steps may be considered from the CAS compliance audit programs). Identify any terminated pension plan costs or credits on the books for this contractor or for acquired or absorbed divisions or other division employees for further review. | audit preparation, cas compliance, compensation limits, compliance critical, high risk, material costs, record keeping | CAS compliance, CAS requirements, FAR and CAS requirements
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Evaluation | 10b. | If the costs are significant (i.e., material and or risk factors have been identified), test contractor contributions under employee pension plans to evidence of payment (i.e., contractor bank statements, electronic funds transfer, or third party payroll processor records). | audit preparation, compensation limits, cost transfers, documentation required, high risk, inter org transfers, labor costs, material costs
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Evaluation | 11 | Health Care Costs. As part of the review of health care costs, verify the contractor included only health insurance premiums and claims for 'eligible dependents'. Request the contractor to demonstrate its procedures for ensuring only costs related to eligible dependents have been included in the proposed allowable costs. Based on the understanding of the contractor's processes and overall risk, design procedures to test proposed allowable costs are related to only eligible dependents. | audit preparation, compliance critical, documentation required, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Evaluation | 12 | IR&D/B&P. If the contractor is identified as a major contractor in the preliminary steps (DFARS 231.205-18(a)), verify the IR&D/B&P costs meet the allowability criteria in DFARS 231.205-18(c). Obtain Costs by Element for each IR&D/B&P project. For significant IR&D projects review the project descriptions, work documents, invention reports to determine if they meet the FAR 31.205-18 and CAS 420 definitions Applied Research, Basic Research, or Development. | audit preparation, cas compliance, cost principles, dfars requirements, documentation required, far compliance, high risk | CAS 420, DFARS 231.205, DFARS 231.205-18, DFARS 231.205-18(a, FAR 31.205, FAR 31.205-18
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Evaluation | 13 | If requested assist audit(s) for significant corporate or home office allocations, or shared service cost allocations were received, compare the allowable costs in the assist audit report(s) to the amounts in the prime / upper-tier segments ICP. Determine the impact, if any, on the final rates. Follow-up on requested assist audits that have not been received. Summarize Results | compliance critical, cost accounting, dcaa coordination, findings potential, high risk, inter org transfers
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Summarize Results | 14 | Verify that any questioned indirect costs also consider directly associated costs that should be questioned/excluded (FAR 31.201-6(a)). | audit preparation, compliance critical, cost principles, cost segregation, far compliance, findings potential, indirect costs, rate development | FAR 31.201, FAR 31.201-6, FAR 31.201-6(a
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | H-01 Indirect Expenses | Summarize Results | 15 | Summarize the results including the conclusions, basis of proposed cost, and audit evaluation. | cost accounting
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Understanding and Planning | 1 | Obtain and document an understanding of contractor internal controls related to interorganizational transfers. • Consideration should be given to any changes in policies for allocating and accumulating costs since the last accounting system audit or incurred cost audit. | cost accounting, documentation required, proposal preparation, system requirements
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Understanding and Planning | 2 | Determine and document the reliability of the information the audit team will use to reach their conclusions in this section. | documentation required
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Understanding and Planning | 3 | • Design Testing Plan
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Evaluation | 5 | Perform substantive analytical procedures based on materiality and risk. | audit preparation, audit process, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Evaluation | 6 | Determine if the selected IOTs were transferred and included in the incurred cost proposal based on costs incurred, as required by FAR 31.205-26(e). If the IOT was transferred and included in the incurred cost proposal based on price (cost plus profit), evaluate compliance with FAR 31.205-26(e)(1) and (2), which provides for an allowance based on price when: | audit preparation, compliance critical, cost accounting, cost principles, far compliance, inter org transfers, proposal preparation | FAR 31.205, FAR 31.205-26
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Evaluation | 6a. | It is the established practice of the transferring organization to price inter-organizational transfers at other than cost for commercial work of the contractor or any division, subsidiary, or affiliate of the contractor under a common control; and | cost accounting, inter org transfers
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Evaluation | 6b. | The items being transferred qualifies for an exception under FAR 15.403-1(b) (supported by adequate price competition or sales data as applicable) and the contracting officer has not determined the price to be unreasonable. | dcaa coordination, executive comp, far compliance | FAR 15.403, FAR 15.403-1
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Evaluation | 7 | Perform the following to assess allowability (FAR 31.201-2) of selected IOTs issued under flexibly priced prime contracts: a. IOT Agreement. Verify a proper agreement exists between the authorizing and performing organizations. b. Based upon how IOT costs are booked/received by the prime segment, design procedures to ensure the proposed / billed IOT costs: • Reconcile to performing segments books or billings (if submitted). • Are in compliance with contractual terms and IOT agreement (i.e., special limitations, T&Mcontracts - FAR 52.232-7 payment clause, etc.) (Note: Depending upon the contractor's specific practices, this may not be feasible without an assist.) Summarize Results | audit preparation, compliance critical, contract terms, cost accounting, cost principles, dcaa coordination, far compliance, inter org transfers, record keeping | FAR 31.201, FAR 31.201-2, FAR 52.232, FAR 52.232-7
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Evaluation | 7a. | IOT Agreement. Verify a proper agreement exists between the authorizing and performing organizations. | audit preparation, contract terms, inter org transfers
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Evaluation | 7b. | Based upon how IOT costs are booked/received by the prime segment, design procedures to ensure the proposed / billed IOT costs: • Reconcile to performing segments books or billings (if submitted). | cost accounting, inter org transfers, record keeping
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Summarize Results | 8 | Incorporate any questioned costs from assist audits received on performing segments and follow-up on any outstanding assist audits. | compliance critical, dcaa coordination, findings potential
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Summarize Results | 9 | Verify that any questioned IOT costs also consider directly associated costs that should be questioned/excluded (FAR 31.201-6(a)). | audit preparation, compliance critical, cost principles, far compliance, findings potential, inter org transfers | FAR 31.201, FAR 31.201-6, FAR 31.201-6(a
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | I-01 Inter-Organizational Transfers (IOTs) | Summarize Results | 10 | Summarize the results including the conclusions, basis of proposed cost, and audit evaluation. | cost accounting
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | U-1 Compensation Reasonableness and FAR Cap Allowability | Summarize Results | 1 | To the extent not already documented in the risk assessment, or labor section D, document your understanding of the contractor's internal controls and basis for proposed compensation. | compensation limits, documentation required, high risk, labor costs
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | U-1 Compensation Reasonableness and FAR Cap Allowability | Summarize Results | 2 | Determine and document the reliability of the information the audit team will use to reach their conclusions in this section. | documentation required
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | U-1 Compensation Reasonableness and FAR Cap Allowability | Summarize Results | 3 | If detailed testing will be performed, document the selection plan and proceed with the steps below. | audit sampling, documentation required
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | U-1 Compensation Reasonableness and FAR Cap Allowability | Evaluate Compensation Using FAR Limits | 4 | Determine applicable FAR 31.205-6(p) Compensation Limitation(s) and determine contractor's compliance with the applicable limitation(s). For each individual selected, question proposed amounts in excess of the limitation(s) as expressly unallowable. | compensation limits, compliance critical, cost principles, far compliance, penalties avoidance | FAR 31.205, FAR 31.205-6
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | U-1 Compensation Reasonableness and FAR Cap Allowability | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 5 | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6(b)(2) considering the following: | audit preparation, compensation limits, cost principles, executive comp, far compliance | FAR 31.205, FAR 31.205-6
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | U-1 Compensation Reasonableness and FAR Cap Allowability | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 5a. | Determine reasonable market survey amounts for total cash compensation (base salary plus short-term bonus). | compensation limits, compliance critical, cost segregation
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | U-1 Compensation Reasonableness and FAR Cap Allowability | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 5b. | Determine if there are any other compensation costs to be considered (e.g. fringe, LTI) and, if so, compute reasonable amounts using market survey data. | compensation limits, compliance critical, indirect costs, rate development
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | U-1 Compensation Reasonableness and FAR Cap Allowability | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 5c. | For each selection, compare total proposed compensation to total reasonable compensation and question the difference after reducing for any computed unallowable costs (from step 4 above) as unreasonable. | audit sampling, compensation limits, compliance critical
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | U-1 Compensation Reasonableness and FAR Cap Allowability | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 6 | Summarize the results including the conclusions, basis of proposed cost, and audit evaluation. | cost accounting
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | A-01 Concluding Steps | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 1 | Summarize and document the audit results and identify the requirements of the audit opinion and using professional judgment select the appropriate opinion based on the evidence obtained. Consider quantitative and qualitative materiality for misstatements (e.g. questioned costs) taken individually, and in aggregate, when evaluating the type of opinion. | audit process, compliance critical, documentation required, findings potential
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | A-01 Concluding Steps | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 2 | Calculate the total questioned costs. Determine if the questioned amounts are material in both the individual cost element and in the aggregate. • Determine if any of the costs questioned are expressly unallowable. (Expressly unallowable costs must be reported to those charged with governance, i.e., The ACO and PCO as applicable) | compliance critical, cost accounting, findings potential, high risk, material costs, penalties avoidance
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | A-01 Concluding Steps | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 3 | Obtain supervisory review of the working papers, and draft audit results section of the audit report before discussions with the contractor. | audit preparation, documentation required, findings potential
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | A-01 Concluding Steps | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 4 | Prepare the draft rate agreement letter, and audit report in accordance with Agency guidance and obtain supervisory review. | audit preparation, contract terms, cost accounting, documentation required, findings potential, labor costs, rate development
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | A-01 Concluding Steps | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 5 | Auditors should document and communicate with the contracting officers upon the completion of our audit and approval of the supervisor. • Coordinate with procurement contracting officers (PCO) for direct costs and administrative contracting officers (ACO) for indirect costs. Request assistance from the FLA or the contractor, if needed. • Coordinate with the cognizant contracting officers (or cognizant auditor) to determine the reporting detail necessary for the contracting officers to make a penalty determination (e.g., Explanatory Notes, Explanatory Notes &Exhibit, etc.) At a minimum, the report should identify questioned costs potentially subject to penalty and include supporting rationale (FAR 42.709-2(b)). | compliance critical, cost segregation, dcaa coordination, documentation required, far compliance, findings potential, indirect costs, material costs, penalties avoidance, rate development, record keeping | FAR 42.709, FAR 42.709-2, FAR 42.709-2(b
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | A-01 Concluding Steps | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 6 | Conduct an exit conference and provide the audit result to the contractor. The contractor's reaction should be obtained for inclusion in the final draft audit report. | audit process, findings potential
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | A-01 Concluding Steps | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 7 | If the contractor does not agree with the questioned cost(s) draft a DCAA Form 1 in accordance withCAM 6-900. [Note: Questioned cost for subcontract effort that is not concurred should be resolved at the prime level (prime contractor and prime's CFAO) using DCAA Form 1 procedures (CAM 6-900). FD Auditors will prepare and send Form 1s applicable to classified contract customers.] | cam reference, compliance critical, contract terms, cost accounting, findings potential, subcontract costs, time reporting |  | CAM 6-900
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | A-01 Concluding Steps | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 8 | Complete the following steps: • Prepare audit lead workflows, as applicable. • Update the contractor permanent file and risk determination for the next fiscal year based on findings/audit results. | high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | A-01 Concluding Steps | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 9 | Prepare and verify accuracy of dollars examined, questioned costs, and sustained questioned costs amounts for DMIS reporting. | audit preparation, compliance critical, findings potential
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | A-01 Concluding Steps | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 10 | If significant instances of CAS noncompliance are found, coordinate and discuss with supervisory auditor and report under activity code 19200 in accordance with Agency guidance. | cas compliance, dcaa coordination, findings potential, high risk
10100 | AP | 6.5 | Jan 2026 | Post Year End Incurred Cost Audit - Small | A-01 Concluding Steps | Review proposed compensation for selected positions for reasonableness per FAR 31.205-6 | 11 | If we identify a business system deficiency during the incurred cost audit, open an 11090 assignment to determine if the deficiency still exists today, and to fully develop and report material weaknesses/significant internal control deficiencies. Note: The issuance of the incurred cost audit is not dependent on the results of the 11090 . | cost accounting, findings potential, high risk, material costs, proposal preparation, system requirements
GovConDash.ai ¦ Government Contracts, Simplified ¦ 114 audit steps across 10 sections ¦ Generated March 27, 2026